## Cover Page
<Question Paper Generation>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Akshat Ruhela
| Role | Team Member
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <Question Paper Generation> Project ID: <CDB21DX044/A034> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Registration | 4
Task_1 | Clicking on the “Register” button should open the Registration form. And User to fill the basic attributes: First Name Last Name DoB Gender Contact Number Email User Id Password Category - User Based on the User Category, the user should be given access privilege |  | AKSHAY | Completed | 5 | 3 | 1 | 0 | 0 | 0
Task_2 | Clicking ‘Submit’ button should validate the datatype constraints for each field And User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red |  | VAIBHAV | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_3 | Post-successful field validation, save the information in the database |  | DIVYA | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_4 | Upon saving the information in the database, display the message “New user created successfully” |  | AKSHAY | Completed | 1 | 0 | 1 | 0 | 0 | 0
User Story #2 | User Authentication | 3
Task_1 | Clicking “Sign In” link should allow the user to enter the User ID and Password and click 2. Portal to validate the entered user |  | DEEPAK | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_2 | Portal to validate the entered user credentials against the database and allow login for registered users. |  | VAIBHAV | Completed | 1 | 0 | 1 | 0 | 0 | 0
Task_3 | If User ID is not present, it should throw error saying " User ID not present. For wrong password, it should say "Password not matching" |  | AKSHAY | Completed | 1 | 0 | 1 | 0 | 0 | 0
User Story #3 | Admin credentials | 5
Task_1 | System should have a Admin Login credentials stored in the DB. Category - Admin |  | AKSHAT | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | When keyed in with correct credentials, it should log in. |  | VAIBHAV | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0
Task_3 | If Admin ID is not present, it should throw error saying " Admin ID not present. For wrong password, it should say "Password not matching" |  | AKSHAT | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0
Task_4 | Admin should have access to check on the help request raised by the user. |  | DIVYA | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0
User Story #4 | Help | 4
Task_1 | Clicking Help should redirect th the Page that allows user to report the technical issues: Issue Description Date of ticket - Auto pupulated |  | DEEPAK | Completed | 3 | 1 | 1.5 | 0 | 0 | 0.5
Task_2 | On submitting the Request ID should be auto generated and tagged to the ticket. The tickets should be saved to the database and admin should have notification in the home page |  | DIVYA | Completed | 3 | 1 | 1 | 1 | 0 | 0
Task_3 | Portal to display the Contact number to report issues. |  | AKSHAT | Completed | 1 | 0 | 1 | 0 | 0 | 0
Task_4 | Resolutions provided by admin should be viewable. |  | DEEPAK | Completed | 1 | 0 | 1 | 0 | 0 | 0
User Story #5 | Resolve help request | 4
Task_1 | Clicking on help request should list all the requests raised by the user. |  | DEEPAK | Completed | 1 | 0 | 0 | 1 | 0 | 0
Task_2 | Clicking the request ID, it should display the details |  | VAIBHAV | Completed | 1 | 0 | 0 | 1 | 0 | 0
Task_3 | Admin should be able to provide resolution |  | DIVYA | Completed | 1 | 0 | 0 | 0 | 1 | 0
Task_4 | The details should be saved to the DB |  | AKSHAY | Completed | 1 | 0 | 0 | 0 | 1 | 1
User Story #6 | Feedback Questionnaire | 3
Task_1 | Admin should be able to create review resources / learnings. Note: Sample questions attached. Can be modified as required. |  | AKSHAT | Completed | 6 | 1 | 2 | 1 | 2 | 0
User Story #7 | User Feedback | 3
Task_1 | User should be able to provide feedback / reviews for the assesment. |  | VAIBHAV | Completed | 6 | 0 | 0 | 0 | 1 | 2
User Story #8 | Trigger Review | 6
Task_1 | When the user logs in after theassesment, system should trigger review / feedback. |  | DIVYA | Completed | 7 | 0 | 2 | 1 | 1 | 4
User Story #9 | Log off | 1
Task_1 | When the user clicks Log off, the system should disconnect from the system. |  | DEEPAK | Completed | 0 | 0 | 0 | 0.5 | 0 | 0.5
User Story #10 | Password reset / Retrieve User ID | 5
Task_1 | During registration, System should pop up three secret questions for Password recovery |  | VAIBHAV | Completed | 2 | 1 | 0 | 1 | 1 | 0
Task_2 | When the user clicks Forgot User ID, system should ask for the secret questions, Contact number / email. On answering the questions correctly, the User ID should be displayed. |  | DEEPAK | Completed | 1 | 0 | 0 | 0 | 1 | 0
Task_3 | When the user clicks Forgot Password, system should ask for the User ID and secret questions. On answering the questions correctly, the password reset page should be displayed. |  | AKSHAT | Completed | 1.5 | 0 | 1 | 0 | 1 | 0.5
Task_4 | On entering the details in the password reset page, password should be validated And On clicking Submit, the details should be saved to the Database |  | DIVYA | Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5
User Story #11 | Add Exam Details | 5
Task_1 | Admin should be able to add exam details |  | AKSHAY | Completed | 8 | 2 | 0 | 2 | 1 | 2
Effort |  |  |  |  | 60 | 46.5 | 29.5 | 21 | 11 | 0
Ideal Effort |  |  |  |  | 60 | 48 | 36 | 24 | 12 | 0

## Sprint -2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #12 | Add Questions and answers | 6
Task_1 | Admin on clicking “Add Question” link should redirect to Question details page. |  | AKSHAY | Completed | 4 | 3 | 1 | 0 | 0 | 0
Task_2 | Admin should be able to add the Question, Answers and the competency. |  | VAIBHAV | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_3 | Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red |  | DIVYA | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_4 | Post-successful field level validation, save the information in the database And Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. |  | DEEPAK | Completed | 1 | 1 | 0 | 0 | 0 | 0
User Story #13 | Map Questions to the topics | 4
Task_1 | When questions are added, it should redirect to the page where all the available topics are listed. |  | VAIBHAV | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0
Task_2 | Admin should be able to select the topic and map the added question. |  | DEEPAK | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0
Task_3 | Clciking Submit should update the mapping to the DB. |  | DEEPAK | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0
User Story #14 | Take assessment | 7
Task_1 | User on clicking Take assessment, it should display the assessments available And User should have option to search for the assessment by entering the assessment code, Skill set |  | AKSHAY | Completed | 3 | 1.5 | 1.5 | 0 | 0 | 0
Task_2 | On searching based on the skill set, it should display all the assessments related to the skill set and the competency level. And User should be able to take the assessment by clicking on the assessment code |  | VAIBHAV | Completed | 3 | 0 | 2 | 1 | 0 | 0
Task_3 | System should pop up message when nearing the time completion |  | AKSHAT | Completed | 2 | 1 | 1 | 0 | 0 | 0
Task_4 | System should abort the test once the time is lapsed |  | DEEPAK | Completed | 2 | 0 | 2 | 0 | 0 | 0
User Story #15 | Test Conduction | 8
Task_1 | System should be able to pick some random question from the question pool based on the subject and difficulty level |  | DIVYA | Completed | 3 | 1 | 1.5 | 0.5 | 0 | 0
Task_2 | System should be able to mark the answered and unanswered questions. |  | DIVYA | Completed | 3 | 0 | 0 | 3 | 0 | 0
Task_3 | System should be able calculate marks based on marking scheme. |  | AKSHAY | Completed | 1 | 0 | 0 | 1 | 0 | 0
Task_4 | System should be able to have a timer so that test will end irrespective of completion of the test. |  | AKSHAT | Completed | 1 | 0 | 0.5 | 0.5 | 0 | 0
User Story #16 | Update Exam details | 6 |  |  | 8
Task_1 | Admin should be able to update the Exam details available in the DB. |  | AKSHAT | Completed | 4 | 0 | 0 | 2 | 2 | 0
Task_2 | Admin should be able to delete the Exam details available in the DB. |  | DEEPAK | Completed | 2 | 0 | 0 | 1 | 1 | 2
Task_3 | On clicking Submit, after validation the details should be saved successfully. |  | AKSHAY | Completed | 1 | 0 | 0 | 0 | 1 | 0
Task_4 | Appropriate messages should be displayed |  | AKSHAY | Completed | 1 | 0 | 0 | 0 | 1 | 0
User Story #17 | Update Questions and Answers | 7
Task_1 | On clicking the questions tab, it should list all the topics available. |  | AKSHAT | Completed | 8 | 2 | 0 | 2 | 4 | 0
Task_2 | Admin on selecting the topic, it should display all the questions mapped to it. |  | AKSHAY | Completed | 8 | 0 | 4 | 0 | 4 | 0
Task_3 | Admin should be able to update the Question and Answers available in the DB. and Admin should be able to delete the Question and Answers available in the DB. |  | DIVYA | Completed | 5 | 1 | 1 | 2 | 1 | 0
Task_4 | On clicking Submit, after validation the details should be saved successfully. and Topics mapped also should be updated if required. |  | AKSHAY | Completed | 4 | 0 | 0 | 0 | 1 | 3
User Story #18 | Evaluate the assessment | 8
Task_1 | When the user clicks Submit Assessment, the system should calculate marks according to marking scheme of the test and questions. |  | VAIBHAV | Completed | 5 | 2 | 0 | 0 | 2 | 2
Task_2 | After Evaluation, it should display the Results to the User. |  | VAIBHAV | Completed | 2 | 0 | 0 | 0 | 1 | 2
Task_3 | System should generate Completion Certificate if the user clears the exam. |  | VAIBHAV | Completed | 1 | 0 | 0 | 0 | 0 | 1
User Story #19 | Assessment report | 8
Task_1 | User on clicking Assessment report should list all the Assessments taken by the user, Mark, Completion status, Date of assessment. |  | DIVYA | Completed | 3 | 0 | 0 | 0 | 1 | 2
Task_2 | On clicking the assessment ID, it should display all the details of the assessment, completion certificate. |  | VAIBHAV | Completed | 3 | 0 | 0 | 0 | 2 | 1
Task_3 | User should have the option to download the certificate as PDF. |  | AKSHAY | Completed | 2 | 0 | 0 | 0 | 0 | 2
User Story #20 | Report Generation | 8
Task_1 | Admin on clicking the Report generation link should display all the assessment codes. and On clicking the assessment code, it should display the count of Users taken the exam, No of Pass, No of fail, Highest score. |  | DIVYA | Completed | 8 | 0 | 2 | 2 | 2 | 2
Task_2 | Admin should have the option to export to excel. and Admin should be able to generate report based on Date Assesment code |  | AKSHAY | Completed | 6 | 0 | 0 | 3 | 1.5 | 1.5
Task_3 | When date option is selected, Admin should be generate report for selected date range, monthly report, report for last 6 months and yearly report |  | AKSHAT | Completed | 2 | 0 | 0 | 0 | 1 | 1
Task_4 | Admin should have the option to generate report of assesment based on total attempts made |  | DEEPAK | Completed | 2 | 0 | 0 | 0 | 1 | 2
User Story #21 | Graphical Representation | 6
Task_1 | System should be able to graphically represent the knowledge of the users according to test taken |  | VAIBHAV | Completed | 3 | 0 | 0 | 1.5 | 0 | 1.5
Task_2 | System should be able to graphically represent the most popular skills or the skills on which most people are taking test. |  | DEEPAK | Completed | 3 | 0 | 0 | 0 | 2 | 2
Task_3 | System should be able to graphically represent the hierarchy of the topics included in a particular skill and also represent that how the skills are interconnected i.e. for learning a skills what all skill you should already possess and learning this skill you will be ready to learn more skills. |  | AKSHAT | Completed | 2 | 0 | 0 | 0 | 2 | 2
EFFORT |  |  |  |  | 110.5 | 95 | 77 | 57.5 | 27 | 0
IDEAL EFFORT |  |  |  |  | 110.5 | 88.4 | 66.3 | 44.2 | 22.1 | 0

## Data (hidden)
In-Progress
Completed
N/A